## Giorgos Stefanis
To-do list
To be completed by: |  | Giorgos Stefanis |  | Name Giorgos Stefanis
Deadline: |  | 2025-10-10 |  | Date 10/10/2025
HOMEWORK 4&5
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Reading/Reviewing Chapters | 09/26/2025 | 2025-10-10 |  | 3 days | Understanding the chapters
100% | Planning | 09/30/2025 | 2025-10-10 |  | 0.5 days | Initial planning
100% | Group Meeting | 2025-06-10 | 2025-06-10 |  | 0.5 days | Initial video call held
100% | Set up To-do list | 2025-06-10 | 2025-06-10 |  | 0.5 days | Downloaded to-do list
100% | Preparation / Setup Azure Notebook | 2025-07-10 | 2025-07-10 |  | 0.5 days | Database connection configuration
100% | Write SQL Queries 1-5 | 2025-07-10 | 2025-08-10 |  | 1 day | Queries drafted
100% | Write SQL Queries 6-10 | 2025-08-10 | 2025-08-10 |  | 1 day | Queries drafted
100% | Group Meeting with Hasan Husseini | 2025-10-10 | 2025-10-10 |  | 0.5 days | Recording and presenting each other's queries
100% | Submit Evrything on github | 2025-10-10 | 2025-10-10 |  | 0.5 days | All requirements are uploaded on github

## Michael cipriani
To-do list
To be completed by: |  | Giorgos Stefanis |  | Name Michael Cipriani
Deadline: |  | 2025-10-10 |  | Date 10/10/2025
HOMEWORK 4&5
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Reading/Reviewing Chapters | 09/26/2025 | 2025-10-10 |  | 4 days | Understanding the chapters
100% | Planning | 09/30/2025 | 2025-10-10 |  | 0.5 days | Initial planning
100% | Group Meeting | 2025-10-06 | 2025-10-06 |  | 0.5 days | Initial video call held
100% | Set up To-do list | 2025-10-06 | 2025-10-06 |  | 0.5 days | Downloaded to-do list
100% | Preparation / Setup Azure Notebook | 2025-10-07 | 2025-10-07 |  | 0.5 days | Database connection configuration
100% | Write SQL Queries 1-5 | 2025-10-08 | 2025-10-08 |  | 0.5 day | Queries drafted
100% | Write SQL Queries 6-10 | 2025-10-08 | 2025-10-09 |  | 1 day | Queries drafted
100% | Group Meeting with Ridhwan Ibrahim | 2025-10-10 | 2025-10-10 |  | 0.5 days | Recording and presenting each other's queries
100% | Submit Evrything on github | 2025-10-10 | 2025-10-10 |  | 0.5 days | All requirements are uploaded on github

## Seeram Govindan
To-do list
To be completed by: |  |  |  | Name Seeram Govindan
Deadline: |  |  |  | Date 10/10/2025
Project 1
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Reading/Reviewing Chapters | 2025-10-06 | 2025-10-07 | 2025-10-07 | 2 days | Understaning chapter 4 and 5
100% | Planning | 2025-10-07 | 2025-10-07 | 2025-10-07 | .5 days | Initial planning
100% | Group Meeting | 2025-10-06 | 2025-10-07 | 2025-10-07 | .5days | Initial video call held
100% | Set up To-do list | 2025-10-06 | 2025-10-06 | 2025-10-07 | .5days | Downloaded to-do list
100% | Preparation / Setup Azure Notebook | 2025-10-07 | 2025-10-07 | 2025-10-07 | .5days | Database connection configuration
100% | Write SQL Queries 1-5 | 2025-10-08 | 2025-10-10 | 2025-10-10 | 1 day | Queries drafted
100% | Write SQL Queries 6 - 10 | 2025-10-08 | 2025-10-10 | 2025-10-10 | 1 day | Queries drafted
100% | Group Meeting with youlun | 2025-10-09 | 2025-10-09 | 2025-10-10 | .5 days | Recording and presenting each other's queries
100% | Submit Evrything on github | 2025-10-10 | 2025-10-10 | 2025-10-10 | 1 day | All requirements are uploaded on github

## Youlun Wang
To-do list
To be completed by: |  |  |  | Name: Youlun Wang
Deadline: |  |  |  | Date
Project 1
% done | Phase | Start By | Original Due By2 | Revised Due By | Number Of Days | Revision Notes
100% | Reading/Reviewing Chapters | 2025-10-06 | 2025-10-07 | 2025-10-07 | 2 days | Understaning chapter 4 and 5
100% | Planning | 2025-10-07 | 2025-10-07 | 2025-10-07 | 1 day | Initial planning
100% | Group Meeting | 2025-10-06 | 2025-10-07 | 2025-10-07 | 1 day | Initial video call held
100% | Set up To-do list | 2025-10-06 | 2025-10-06 | 2025-10-07 | 1 day | Downloaded to-do list
100% | Preparation / Setup Azure Notebook | 2025-10-07 | 2025-10-07 | 2025-10-07 | 1 day | Database connection configuration
100% | Write SQL Queries 1-5 | 2025-10-08 | 2025-10-10 | 2025-10-10 | 1 day | Queries drafted
100% | Write SQL Queries 6 - 10 | 2025-10-08 | 2025-10-10 | 2025-10-10 | 1 day | Queries drafted
100% | Group Meeting with Seeram | 2025-10-09 | 2025-10-09 | 2025-10-10 | 1 day | Recording and presenting each other's queries
100% | Submit Evrything on github | 2025-10-10 | 2025-10-10 | 2025-10-10 | 1 day | All requirements are uploaded on github

## Hasan Husseini
To-do list
To be completed by: |  |  |  | Name Hasan Husseini
Deadline: |  |  |  | Date 9-0ct-25
Project 1
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Read Textbook | 2025-09-26 | 2025-10-06 |  | 1 | Build chapter comprehension
100% | Plan | 2025-10-06 | 2025-10-06 |  | <1 | Assign partners
100% | Group Meeting | 2025-10-06 | 2025-10-06 |  | <1 | Initial call
100% | To-Do List | 2025-10-07 | 2025-10-07 |  | <1 | Setup to-do list
100% | Setup Azure Notebook | 2025-10-08 | 2025-10-08 |  | <1 | Install Azure
100% | Write Queries | 2025-10-09 | 2025-10-09 |  | 1 | Drafted & tested all 10 queries
100% | Group Meeting with Giorgos Stefanos | 2025-10-09 | 2025-10-09 |  | <1 | Presentation video recording
100% | Edit & upload group YouTube video | 2025-10-10 | 2025-10-10 |  | <1 | Edited recording
100% | Submit all on GitHub | 2025-10-10 | 2025-10-10 |  | <1 | Push

## Ridhwan Ibrahim
To-do list
To be completed by: |  |  |  | Name Ridhwan Ibrahim
Deadline: |  |  |  | Date 10/10/2025
HOMEWORK 4&5
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Reading/Reviewing Chapters | 2025-09-26 | 2025-10-10 |  | 4 days | Understanding the chapters
100% | Planning | 2025-09-30 | 2025-10-10 |  | 0.5 days | Initial planning
100% | Group Meeting | 2025-10-06 | 2025-10-06 |  | 0.5 days | Initial video call held
100% | Set up To-do list | 2025-10-06 | 2025-10-06 |  | 0.5 days | Finalized to-do list
100% | Preparation / Setup Azure Notebook | 2025-10-07 | 2025-10-07 |  | 0.5 days | Database connection configuration
100% | Write SQL Queries 1-5 | 2025-10-08 | 2025-10-08 |  | 0.5 days | Queries drafted
100% | Write SQL Queries 6-10 | 2025-10-08 | 2025-10-09 |  | 0.5 days | Queries drafted
100% | Group Meeting with Micheal Cipriani | 2025-10-10 | 2025-10-10 |  | 0.5 days | Recording and presenting each other's queries
100% | Submit Evrything on github | 2025-10-10 | 2025-10-10 |  | 0.5 days | All requirements are uploaded on github